## Weekly_Status
Week # | Activity/Task | Next Steps/Plan | Impediments/Blockers
Week of 01-Apr-2022 to 07-Apr-2022 | Incorporated the VINGC SCRIPTS and UNINSTALL VINGC CLUSTER USING HELM (Uninstall ViNGC using helm, Uninstall Couchbase, Uninstall NFS, Uninstall ViNGC configuration )process in the cloud native document. Incorporating the Network Diagram and the document shared by Josh from Turnium into cloud native document. Self Reviewiing the incorporated topics in the cloud native document. Completed the self review of cloud native document and send for Review.
Week of 25-Mar-2022 to 31-Mar-2022 | From Altran 5GC perspective, incorporated the below processes in the cloud native document draft 0.3. • All The Hardware, Software, External IP Address and Node Port Requirements • All The Variable Terms (Name Space & Helm Release Name) And the Vingc Deployment Process (Configure Name Space and Service Account, NFS Logging, Couchbase Setup & Deployment, NGC Setup & Deployment,) • VINGC BASIC NF CONFIGURATION And VINGC HTTPS CONFIGURATION Process • Environment Variables and Running the Vingc Containers with Docker-Compose Process • Multiple Slice Deployment (Addition of Slice, New Slice For AMF, SMF & UPF NF Deployment Sample Values and Removal of Slice) And Multiple Tenant Deployment (Addition Of Tenant, Removal Of Tenant And Restart of Tenant) Process.
Week of 18-Mar-2022 to 24-Mar-2022 | Public Holiday on 18th Mar 2022 Had call with Rajat from Capgemini for Altran 5GC. Created a rough draft of the KT given by Rajat from capgemini on Altran 5GC. Converted Slicing Templates (Design Time) (Taken content from Youtube, Rajendher Mishra from Arna Networks has taken session on this) rough draft in to main document (Cloud Native 5G Super Blueprint_Draft 0.3) Converted the rough draft of Altran 5GC into "Cloud Native 5G Super Blueprint_Draft 0.3" document. Incorporating the content from the document provided by Rajat (Capgemini) for Altran 5GC into cloud native document.
Week of 11-Mar-2022 to 17-Mar-2022 | Inserting all the Figure and Table caption in the cloud Native document draft 0.2. Reviewing the incorporated content given by Rebaca and Kaloom in Cloud Native Document. Personal Leave on 14th March 2022 Updated the cloud native document draft 0.2 by adding the high-level flow diagram of "ONAP with ALRAN 5G Core and Kaloom UPF" and its explanation. Self Reviewed the complete "Cloud Native 5G Super Blueprint_Draft 0.2" document. Sent the "Cloud Native 5G Super Blueprint_Draft 0.2" document for review. Creating draft for Slicing Templates (Design Time) (Taken content from Youtube, Rajendher Mishra from Arna Networks has taken session on this). Below is the youtube link. https://www.youtube.com/watch?v=pUlfcGyFCFo&t=153s
Week of 04-Mar-2022 to 10-Mar-2022 | Completed creating the rough draft and Updated the information given by Copus & Ganesh from Kaloom into cloud native document. Incorporating the content from the document provided by Kaloom (Sandeep) into cloud native document. Completed incorporating the content and the document provided by Kaloom (Ganesh & Copus) in to Cloud Native Document. Incorporating the content from the document provided by Rebaca into cloud native document. Completed incorporating the document provided by Rebaca in to Cloud Native Document.
Week of 25-Feb-2022 to 03-Mar-2022 | Reviewed the cloud native document for any missing information and commented on it to reach out to the respective owners. 28/02/2022 was Public holiday Had call with Ganesh & Copus from Kaloom to get KT on 5G SBP Cloud Native demo Understanding the documents provided by Rebaca that which content needs to be updated in the Cloud Native Document. Creating the rough draft from the KT given by Copus & Ganesh from Kaloom on cloud native demo documentation | Once Rajat from Altran provides his time slot, will schedule session with him. Scheduled call with Sandeep (Turnium) on 9th Mar 2022
Week of 18-Feb-2022 to 24-Feb-2022 | Updated the EMCOUI deployment process with screen shots in the cloud native documentation. Had call with Hanen and he explained the ppt slides (5G Cloud Native Network) Converted the explanation given by Hanen on "5G Cloud Native Network" slides to rough draft. Converting the rough draft of Hanen's KT to the cloud native document.
Week of 11-Feb-2022 to 17-Feb-2022 | Incorporated the changes given by Sriram for the ONAP cloud Native Documentation. Updated the screen shots of the EMCO deployment process which was provided by Rohit (Complete screeen shots yet to be provided) Updated the highlevel architecture diagram and the explanation for cloud native 5G super blueprint Personal Leave on 17/02/2022 Trying to understand the ppt slides provided by Hanen. Updating the Cloud Native Document. (Adding Abot information)
Week of 04-Feb-2022 to 10-Feb-2022 | Learning about Redhat and it installation guide (https://access.redhat.com/documentation/en-us/red_hat_enterprise_linux/7/html/installation_guide/index) Had call with Hanen to document the Redhat openshift integration part in the 5G Super Blueprint demo held on Oct2021 Created the draft for abot testing done after Orchestrating the 5G core (Demo video link was shared by Sriram) Created a rough draft from Hanen's call Updated the Abot testing process in the main document. Understanding the Redhat Openshift/Kubernetes/Docker |  | Yet to get the the build and deploy image in helm chart for EMCO & EMCOUI with the screen shots. (EMCO & EMCOUI installation)
Week of 28-Mar-2022 to 03-Feb-2022 | Creating the rough draft of the slicing orchestrator (ONAP_5G Super Blueprint) Completed documenting the Network Slicing Orchestration (ONAP) Started working on Orchestrating the 5G core (ONAP) Updated the piece of content for the Orchestrating the 5G core in the document | Convert the rought draft into main document. Start working on Orchestrating the 5G core (ONAP) Update the Orchestrating the 5G core (ONAP) content as discussed with Sandeep. Tapas will provide the build and deploy image in helm chart for EMCO & EMCOUI with the screen shots | The demo link which was send by Sandeep is not related to the 5G Super Blueprint demo, so asked him for the related video. The video will be given by Sandeep on 4th Feb 2022. Had confussions in the github emco repository link, so had call with sandeep and got is clarified. Waiting for the demo video from Sandeep for Orchestrating the 5G core.
Week of 21-Jan-2022 to 27-Jan-2022 | Understanding the demo of ONAP with 5G cloud native where the respective link was given by Sriram. Understanding how Cloud Native 5G Blueprint Network Slicing is done. (Demo) Learning on how ONAP setup is done (Installation and Configuration from ONAP site) Understanding the EMCO installation procedure (Doc link was shared by Sriram) Learning on EMCO Architecture and design (wiki.onap.org) Creating the rough draft of the demo given by Amar on Cloud Native 5G Blueprint Network Slicing. | Understand how Cloud Native 5G Blueprint Network Slicing is done. (Demo) How ONAP setup is done (Installation and Configuration) Understand EMCO Start the initial draft document of LFN blueprint demo given by ONAP
Week of 14-Jan-2022 to 20-Jan-2022 | Learning about ONAP Learning on ONAP Architecture and ONAP Blueprint Learning on ONAP Architecture and ONAP Modelling Had call with Sriram for an Introduction with ONAP on 5G Cloud Native Learnt on Overall High level view for ONAP-based Slice Management from WIKI.ONAP.ORG | Learn on ONAP Architecture and ONAP Blueprint Learn on ONAP Architecture and ONAP Modelling Call with Sriram for an Introduction with ONAP on 5G Cloud Native Learn on Overall High level view for ONAP-based Slice Management from WIKI.ONAP.ORG Understand the demo of ONAP with 5G cloud native where the respective link will be given by Sriram

## KT_Details
Date of KT | Company | KT/Interview Title | Interviewer | Link to Access | Note | Comment
2022-01-21 | Arnanetworks | 2022-Jan-21_ONAP_Introduction_5G Cloud Native Network Documentation | Sriram | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EbUUDfISGctKkihwsxJnoWUB5jNlYunMgX9qHoG0O1xMHg?e=P8sgLl | Sriram has shared the wiki link of the demo
2022-01-31 | Arnanetworks | Session 1_2022-Jan-31_ONAP 5G Cloud Native Network Documentation | Sriram/Sandeep | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/ERpYyPiojgpLiGRaAEcwrQEBzORqhg-ySBVdWC9HNN2jGA?e=KhnlsY | Discussed on the wiki link shared by Sriram and in this meeting sriram asked sandeep to give the new demo video for 5GC Orchestration and github repository for EMCO & EMCOUI build and deployment process
2022-02-03 | Arnanetworks | Session 2_2022-Feb-03_ONAP 5G Cloud Native Network Documentation | Sandeep | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EailHDGHFMpIgSRvhK7HEmoBf9RGShpWqO7pMfgtxUVfSQ?e=PrrdsQ | Sandeep has shared the github repository link for EMCO & EMCOUI build and deployment process and he said he will create a new video for 5GC orchestration and send us. | New video for 5GC orchestration is not shared. Sriram asked to Scheduled call on 11th Feb 2022, where he will take through the steps.
2022-02-07 | Redhat | Session 1_2022-Feb_07_Redhat_5G Cloud Native Network Demo Documentation | Hanen | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/Eb3q7xkuwFtFgJjzoc5LOd8BIJ9l40FdtXuuubyGRkpFUA?e=ineQwp | Hanen has given highlevel overview of the process done by Redhat in 5GS Blueprint and he said we will share some slides and the big picture networking diagrams.
2022-02-11 | Arnanetworks | Session 3_2022-Feb-11_ONAP 5G Cloud Native Network Documentation | Sriram | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EYrq_qW9KCZPlF9a2uwUfxsBZ8gIWJm-UML9chrwxxTFfw?e=Do9W71 | Sriram has given some changes to the ONAP cloud native document and he said he will give the lessons learnt. He has also given the (ritu.sood@intel.com) mail id, to clarify the doubts on EMCO & EMCOUI build and deploy process.
2022-02-21 | Redhat | Session 2_2022-Feb_21-5G Cloud Native Network.ppt Explanation_Redhat | Hanen | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/ERW7oln3wt9Gk3rVRP-a0uwBZ-xGYNsWeNSOhTFDVvgy2g?e=rbiILz | Hanen has explained the PPT (5G Cloud Native Network) and he said he will provide the Main components of the openshift that were used for the POC. | Hanen has to provide the below information. * The Main components of the Openshift that were used for the POC (Cloud Native Demo held on October 2021) * Issues Encountered * Workarounds * Mitigations * Lessons Learned
2022-03-01 | Kaloom | Session 1_2022-Mar-01_5G Cloud Native Network Documentation_Kaloom | Ganesh/Copus | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EWMG0EJMONJBnrC2eUtaSu4BTmIxmJ_UND3cf6F15DsbXg?e=vgQN6m | Ganesh & Copus has given the highlevel explanation of the process which they have done in 5G SBP Cloud Native Demo held on October 2021 | Copus will provide the required files for the docuemntation in two days
2022-03-09 | Turnium | Session 1_09-Mar-2022_5G Cloud Native Network Demo Documentation-(SD-WAN) | Sandeep/Josh | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/ESWcWAE96sdJjSAcKaun-j4Bz1A8QCstFNS7MmQEiu-qSQ?e=qhUn6c | We from Wavelabs has explained Sandeep & Josh for what are all the inputs needed for the 5G Cloud Native demo documention (Demo held on october 2021) | Josh will share the document in a week with the required input for 5G Cloud Native demo documentation
2022-03-21 | Capgemini | Session 1_21-Mar-2022_5G Cloud Native Network Demo Documentation-Altran 5G Core | Rajat Gupta | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EeNnYSJTGkFApTf-DBxaIlsB2yhD_UU0gSLAWMIA02U8-g?e=CW2uot | Rajat has explained on a high-level of how Altran 5GC work in Kaloom lab and he has shared the required documents.
2022-04-06 | A10 | Session 1_06-Apr-2022_5G Cloud Native Network Demo Documentation-(A10) | Konstantin/Adil Baghir | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EdwFI7HfQ55Mu60OzuTmU8YBVeYu1Zk4xDx3KtuXUauC8w?e=UiRiI1 | We from Wavelabs has explained what is the requirement for the 5G Cloud Native demo documention (Demo held on october 2021) from A10 | Konstantin will create a rough draft and will share it with wavelabs on 11th Mar 2022.

## Links
Date | Received from | Link | Short Description | Additional notes | Comments
2022-01-21 | Sriram (ONAP) | https://docs.onap.org/en/istanbul/ | The official documentation of ONAP and this link is for the latest Istanbul release.
2022-01-24 | Sriram (ONAP) | https://wiki.opnfv.org/pages/viewpage.action?pageId=63111404 | Instructions on Setting up the 5G Cloud Native Network + ONAP Demo | Wiki Link | This is the old link and the content in this was created on 20th Oct 2020 | Documentation Recording Folder | https://wavelabstechnologies-my.sharepoint.com/:f:/g/personal/shanmuga_sundaram_wavelabs_ai/En1sKqZAB_tHiaUgUPUdFdABvk4uW9IG0OZkgRKMHJeUVg?e=inRuVU
2022-02-02 | Sandeep Sharma (ONAP) | https://gitlab.com/project-emco | The GitHub repository for the new EMCO project. |  |  | KT Details | https://wavelabstechnologies-my.sharepoint.com/:x:/g/personal/shanmuga_sundaram_wavelabs_ai/EauZm_lUA0NHpm5fBJtXCicBGWBLo5c5RhF-0gCshAfO4w?e=BDCtGl
2022-10-12 |  | https://www.youtube.com/watch?v=CIEmb0jGa7A | ONE Summit 2021 Cloud Native 5G Blueprint Network Slicing Demo. This video demo was given by Amar and confirmed with Sriram to update the same in the documentation. | Youtube Link
|  | https://docs.onap.org/en/latest/guides/onap-operator/settingup/index.html | Settingup of ONAP | Official ONAP wesite. Checked with Sriram and updated the link in the documentation
|  | https://docs.onap.org/projects/onap-oom/en/latest/oom_quickstart_guide.html#quick-start-label | (OOM Quick Start Guide) The instructions to deploy ONAP | Official ONAP wesite
2022-02-25 | Louis | https://wiki.lfnetworking.org/x/MAzoAw | Documentation provided by Rebaca which has information about Abot & Gnb.