## Weekly_Status
Week # | Activity/Task | Next Steps/Plan | Impediments/Blockers
Week of 21-Feb-2022 to 25-Feb-2022 | Updated the EMCOUI deployment process with screen shots in the cloud native documentation. Had call with Hanen and he explained the ppt slides (5G Cloud Native Network) Converted the explanation given by Hanen on "5G Cloud Native Network" slides to rough draft. Converting the rough draft of Hanen's KT to the cloud native document.
Week of 14-Feb-2022 to 18-Feb-2022 | Incorporated the changes given by Sriram for the ONAP cloud Native Documentation. Updated the screen shots of the EMCO deployment process which was provided by Rohit (Complete screeen shots yet to be provided) Updated the highlevel architecture diagram and the explanation for cloud native 5G super blueprint Personal Leave on 17/02/2022 Trying to understand the ppt slides provided by Hanen. Updating the Cloud Native Document. (Adding Abot information)
Week of 07-Feb-2022 to 11-Feb-2022 | Learning about Redhat and it installation guide (https://access.redhat.com/documentation/en-us/red_hat_enterprise_linux/7/html/installation_guide/index) Had call with Hanen to document the Redhat openshift integration part in the 5G Super Blueprint demo held on Oct2021 Created the draft for abot testing done after Orchestrating the 5G core (Demo video link was shared by Sriram) Created a rough draft from Hanen's call Updated the Abot testing process in the main document. Understanding the Redhat Openshift/Kubernetes/Docker |  | Yet to get the the build and deploy image in helm chart for EMCO & EMCOUI with the screen shots. (EMCO & EMCOUI installation)
Week of 31-Jan-2022 to 04-Feb-2022 | Creating the rough draft of the slicing orchestrator (ONAP_5G Super Blueprint) Completed documenting the Network Slicing Orchestration (ONAP) Started working on Orchestrating the 5G core (ONAP) Updated the piece of content for the Orchestrating the 5G core in the document | Convert the rought draft into main document. Start working on Orchestrating the 5G core (ONAP) Update the Orchestrating the 5G core (ONAP) content as discussed with Sandeep. Tapas will provide the build and deploy image in helm chart for EMCO & EMCOUI with the screen shots | The demo link which was send by Sandeep is not related to the 5G Super Blueprint demo, so asked him for the related video. The video will be given by Sandeep on 4th Feb 2022. Had confussions in the github emco repository link, so had call with sandeep and got is clarified. Waiting for the demo video from Sandeep for Orchestrating the 5G core.
Week of 24-Jan-2022 to 28-Jan-2022 | Understanding the demo of ONAP with 5G cloud native where the respective link was given by Sriram. Understanding how Cloud Native 5G Blueprint Network Slicing is done. (Demo) Learning on how ONAP setup is done (Installation and Configuration from ONAP site) Understanding the EMCO installation procedure (Doc link was shared by Sriram) Learning on EMCO Architecture and design (wiki.onap.org) Creating the rough draft of the demo given by Amar on Cloud Native 5G Blueprint Network Slicing. | Understand how Cloud Native 5G Blueprint Network Slicing is done. (Demo) How ONAP setup is done (Installation and Configuration) Understand EMCO Start the initial draft document of LFN blueprint demo given by ONAP
Week of 17-Jan-2022 to 21-Jan-2022 | Learning about ONAP Learning on ONAP Architecture and ONAP Blueprint Learning on ONAP Architecture and ONAP Modelling Had call with Sriram for an Introduction with ONAP on 5G Cloud Native Learnt on Overall High level view for ONAP-based Slice Management from WIKI.ONAP.ORG | Learn on ONAP Architecture and ONAP Blueprint Learn on ONAP Architecture and ONAP Modelling Call with Sriram for an Introduction with ONAP on 5G Cloud Native Learn on Overall High level view for ONAP-based Slice Management from WIKI.ONAP.ORG Understand the demo of ONAP with 5G cloud native where the respective link will be given by Sriram

## KT_Details
Date of KT | Company | KT/Interview Title | Interviewer | Link to Access | Note | Comment
2022-01-21 | Arnanetworks | 2022-Jan-21_ONAP_Introduction_5G Cloud Native Network Documentation | Sriram | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EbUUDfISGctKkihwsxJnoWUB5jNlYunMgX9qHoG0O1xMHg?e=P8sgLl | Sriram has shared the wiki link of the demo
2022-01-31 | Arnanetworks | Session 1_2022-Jan-31_ONAP 5G Cloud Native Network Documentation | Sriram/Sandeep | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/ERpYyPiojgpLiGRaAEcwrQEBzORqhg-ySBVdWC9HNN2jGA?e=KhnlsY | Discussed on the wiki link shared by Sriram and in this meeting sriram asked sandeep to give the new demo video for 5GC Orchestration and github repository for EMCO & EMCOUI build and deployment process
2022-02-03 | Arnanetworks | Session 2_2022-Feb-03_ONAP 5G Cloud Native Network Documentation | Sandeep | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EailHDGHFMpIgSRvhK7HEmoBf9RGShpWqO7pMfgtxUVfSQ?e=PrrdsQ | Sandeep has shared the github repository link for EMCO & EMCOUI build and deployment process and he said he will create a new video for 5GC orchestration and send us. | New video for 5GC orchestration is not shared. Sriram asked to Scheduled call on 11th Feb 2022, where he will take through the steps.
2022-02-07 | Redhat | Session 1_2022-Feb_07_Redhat_5G Cloud Native Network Demo Documentation | Hanen | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/Eb3q7xkuwFtFgJjzoc5LOd8BIJ9l40FdtXuuubyGRkpFUA?e=ineQwp | Hanen has given highlevel overview of the process done by Redhat in 5GS Blueprint and he said we will share some slides and the big picture networking diagrams.
2022-02-11 | Arnanetworks | Session 3_2022-Feb-11_ONAP 5G Cloud Native Network Documentation | Sriram | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EYrq_qW9KCZPlF9a2uwUfxsBZ8gIWJm-UML9chrwxxTFfw?e=Do9W71 | Sriram has given some changes to the ONAP cloud native document and he said he will give the lessons learnt. He has also given the (ritu.sood@intel.com) mail id, to clarify the doubts on EMCO & EMCOUI build and deploy process.
2022-02-21 | Redhat | Session 2_2022-Feb_21-5G Cloud Native Network.ppt Explanation_Redhat | Hanen | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/ERW7oln3wt9Gk3rVRP-a0uwBZ-xGYNsWeNSOhTFDVvgy2g?e=rbiILz | Hanen has explained the PPT (5G Cloud Native Network) and he said he will provide the Main components of the openshift that were used for the POC. | Hanen has to provide the below information. * The Main components of the Openshift that were used for the POC (Cloud Native Demo held on October 2021) * Issues Encountered * Workarounds * Mitigations * Lessons Learned
2022-03-01 | Kaloom | Session 1_2022-Mar-01_5G Cloud Native Network Documentation_Kaloom | Ganesh/Copus | https://wavelabstechnologies-my.sharepoint.com/:v:/g/personal/shanmuga_sundaram_wavelabs_ai/EWMG0EJMONJBnrC2eUtaSu4BTmIxmJ_UND3cf6F15DsbXg?e=vgQN6m | Ganesh & Copus has given the highlevel explanation of the process which they have done in 5G SBP Cloud Native Demo held on October 2021 | Copus will provide the required files for the docuemntation in two days

## Links
Date | Received from | Link | Short Description | Additional notes | Comments
2022-01-21 | Sriram (ONAP) | https://docs.onap.org/en/istanbul/ | The official documentation of ONAP and this link is for the latest Istanbul release.
2022-01-24 | Sriram (ONAP) | https://wiki.opnfv.org/pages/viewpage.action?pageId=63111404 | Instructions on Setting up the 5G Cloud Native Network + ONAP Demo | Wiki Link | This is the old link and the content in this was created on 20th Oct 2020 | Documentation Recording Folder | https://wavelabstechnologies-my.sharepoint.com/:f:/g/personal/shanmuga_sundaram_wavelabs_ai/En1sKqZAB_tHiaUgUPUdFdABvk4uW9IG0OZkgRKMHJeUVg?e=inRuVU
2022-02-02 | Sandeep Sharma (ONAP) | https://gitlab.com/project-emco | The GitHub repository for the new EMCO project. |  |  | KT Details | https://wavelabstechnologies-my.sharepoint.com/:x:/g/personal/shanmuga_sundaram_wavelabs_ai/EauZm_lUA0NHpm5fBJtXCicBGWBLo5c5RhF-0gCshAfO4w?e=BDCtGl
2022-10-12 |  | https://www.youtube.com/watch?v=CIEmb0jGa7A | ONE Summit 2021 Cloud Native 5G Blueprint Network Slicing Demo. This video demo was given by Amar and confirmed with Sriram to update the same in the documentation. | Youtube Link
|  | https://docs.onap.org/en/latest/guides/onap-operator/settingup/index.html | Settingup of ONAP | Official ONAP wesite. Checked with Sriram and updated the link in the documentation
|  | https://docs.onap.org/projects/onap-oom/en/latest/oom_quickstart_guide.html#quick-start-label | (OOM Quick Start Guide) The instructions to deploy ONAP | Official ONAP wesite
2022-02-25 | Louis | https://wiki.lfnetworking.org/x/MAzoAw | Documentation provided by Rebaca which has information about Abot & Gnb.